| INA - Industrija nafte d.d. Industrial & Corporate Services Procurement |  |
| --- | --- |
| Av. Većeslava Holjevca 10 10 000 Zagreb +385 91 495 0488 Naš znak – Re: WS3222425992 Datum – Date: 13.7.2026. |  |

INVITATION FOR OPEN TENDERING

APH – Air pre-heating system revitalisation on the vacuum distillation furnace (323-H-001)

INA No. WS3222425992

Purchaser: INA-INDUSTRIJA NAFTE d.d.,

Av. V. Holjevca 10, 10020 Zagreb

MB: 3586243; OIB: 27759560625

Tel: +385 91 495 0488; e-mail: dubravka.drndelic@ina.hr

- Procurement subject: The subject-matter of procurement is the preparation of detailed designs, procurement and delivery of equipment and materials, execution of works, commissioning and preparation of the as-built design for the Processing furnace efficiency improvement project 323-H-001 at the Rijeka Oil Refinery according to the “turnkey” principle

- Time of works execution:  The deadline for the execution of the contractual obligations has been divided into several segments, as follows:

•	Submission of a detailed schedule for the execution of works, elaborated up to level 4: no later than one hundred and twenty (120) calendar days upon the signing of the contract. Delivery of the LEVEL V schedule plan (works suspended) delivery no later than 01.09.2027

•	Planned commencement of works, 01.02.2028

•	Mechanical completion of works, 25.03.2028 (not later than 50 calendar days from the start of works)

•	Examination of project parameters, 05.04.2028 (no later than 10 calendar days from the achievement of mechanical completion of the works)

•	Delivery of the as-built design (final version of all folders) and quality proof documentation, 01.04.2028

•	Use permit obtained and all deficiencies eliminated, 31.01.2029.

- Place of service execution:  The Works will be executed at the following location:  Rijeka Refinery, Urinj 53, 51 221 Kostrena

- Tender documentation may be acquired by sending an inquiry to the following e-mail address: dubravka.drndelic@ina.hr

- If you are not registered in the Ariba system, please register on following page:

https://www.ina.hr/ariba

- Bid delivery date: 10.8.2026. until 12:00 (Croatia local time) (in the Ariba system).

- Contact: Dubravka Drndelić; e-mail: dubravka.drndelic@ina.hr ; tel +385 91 495 0488

More at www.ina.hr