## Cover sheet
	external partner logo

PROGRESS REPORT

full project title

External partner name

Number of report:	no / year	Date:	21.1.2020

## General overview
	Project general overview

Scope of work:

		INA signature date:		External partner signature date:					Contract deadline:

Contract signature:

External partners obligations, liabilities according to the subject contract:

Summary of everything done so far related to the subject contract:

## Contract cost & schedule mgmt
	Contract cost & schedule management

No	Contract number	Supplier	Contracted amount	Realized amount	Realized / Contracted	Kickoff meeting	Scheduled Start	Actual Start	Scheduled Finish	Actual Finish	Scheduled Total days	Actual Total days	Delay from scheduled finish
1					#DIV/0!					0	0	0
2					#DIV/0!					0	0	0
3					#DIV/0!					0	0	0
4					#DIV/0!					0	0	0
5						0	0	0
6						0	0	0
7						0	0	0
8						0	0	0
9						0	0	0
10						0	0	0

	Invoicing Plan (Payment milestones)
						HRK
		YEAR 1
		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
Plan
Actual
Difference		0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00

		YEAR 2

		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
Plan
Actual
Difference		0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00

		YEAR 3

		Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
Plan
Actual
Difference		0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00	0,00

## Communication list
Communication list

Company / Person	Position in the company	Role in the project	E-mail	Phone / Mobile
INA d.d.

Contractor ???

## Material & equipment report
Partner:
Owner:	INA Industrija nafte d.d. Zagreb Croatia				CONTRACTUAL DELIVERY DATE:
Location:					CONTRACTUAL Shipping:
Project IM position:
Project name:
Scope of delivery:					DELIVERY DATE (Target)
Contract No.:					DELIVERY DATE (Current schedule)
					DELIVERY Shipping:

Project name
(% COMPLETE)

STATUS	GENERAL ARRANGEMENT		RAW MATERIALS		ASSEMBLY and		FINAL
DATE	DRAWINGS		RECEIVED		INSPECTION		DOCUMENTATION
	PLANNED	ACTUAL	PLANNED	ACTUAL	PLANNED	ACTUAL	PLANNED	ACTUAL

COMPLETION DATE
SCHEDULED
NEW FORECAST
ACTUAL

		-- Signifies updates during this period

Significant accomplishments during the reporting month in each key category:

Significant activities planned for the next month:

A log of approved and pending scope changes:

Action Item List:

This monthly report is a consolidation of cost and schedule status for the engineering, procurement & installation/works phases of the project.

Attachments
1. Work Breakdown Structure					Signature
2. Project Summary Schedule (Master Schedule)

## S curve monthly
			PROJECT TITLE:

CONTRACTOR & CONTRACT NUMBER

ACTUAL START						ACTUAL COMPLETION					CONTRACTED START					CONTRACTED COMPLETION

Monthly S curve / %

MAIN ACTIVITIES IN THE SUBJECT PERIOD

MAIN ACTIVITIES IN THE NEXT PERIOD

Prepared by:			Name and surname:					Signature:					21.1.2020

## Input S curve - monthly
			Year 1					Year 2					Year					Year 3
Months		Start date / (month end input)	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
Planned %			0,0%
Actual %			0,0%

## S curve daily - weekly
			PROJECT TITLE:

CONTRACTOR & CONTRACT NUMBER

ACTUAL START						ACTUAL COMPLETION					CONTRACTED START					CONTRACTED COMPLETION

S - curve / %

MAIN ACTIVITIES IN THE SUBJECT PERIOD

MAIN ACTIVITIES IN THE NEXT PERIOD

Prepared by:			name:					signature:					21.1.2020

## Input S curve - daily; weekly
	Select the progress monitoring method from the menu in cell E2:			1

	daily		Start date / (report input date)	1.10.13	2.10.13	3.10.13	4.10.13	5.10.13	6.10.13	7.10.13	8.10.13	9.10.13	10.10.13	11.10.13	12.10.13	13.10.13	14.10.13	15.10.13	16.10.13	17.10.13	18.10.13	19.10.13	20.10.13	21.10.13	22.10.13	23.10.13	24.10.13	25.10.13	26.10.13	27.10.13	28.10.13	29.10.13	30.10.13	31.10.13	1.11.13	2.11.13	3.11.13	4.11.13	5.11.13	6.11.13	7.11.13	8.11.13	9.11.13	10.11.13	11.11.13	12.11.13	13.11.13	14.11.13	15.11.13	16.11.13	17.11.13	18.11.13	19.11.13	20.11.13	21.11.13	22.11.13	23.11.13	24.11.13	25.11.13	26.11.13	27.11.13	28.11.13	29.11.13	30.11.13	1.12.13

	plan %			0,0%
	actual %			0,0%

daily	1
weekly	7
two-week	14

##  Minimum Tracking Activities
No	Activity name	Completion / %			PLANNED DATES				ACTUAL DATES			COMMENT			PROGNOZIRANI DATUM (Forecast)
					START		COMPLETION		START		COMPLETION				START				KRAJ
	PROJECT PLAN
1	PREPARATION PHASE
1.1	Engineering design
1.1.1	Kick off meeting
1.1.2	Design input data preparation
1.1.3	Study (HAZOP, Process revamp, feasibility, etc.)
1.1.4	Conceptual design
1.1.5	Location permit issuing
1.1.6	Main design
1.1.7	Building permit issuing
1.1.8	Detail design
1.1.9	Tender preparation for key equipement
1.1…..	……….. other
2	IMPLEMENTATION PHASE
2.1	Kick off meeting - key equipment delivery
2.2	Delivery of documentation for key equipment
2.3	Delivery of key equipment (specify which)
2.3.1	Delivery of key equipment 1
2.3.2	Delivery of key equipment 2
2.3.3	Delivery of key equipment 3
2.3….	……….. other
2.4	Works execution (specify which type of works)
2.4.1	Kick off meeting - works execution
2.4.2	Materials purchasing
2.4.3	Prefabrication
2.4.4	Construction site registration
2.4.5	Mobilization of construction site
2.4.6	Scaffolding
2.4.7	Dismantling works
2.4.8	Mounting works
2.4.8.1	Installation of key equipment 1 (specify which exactly)
2.4.8.2	Installation of key equipment 2 (specify which exactly)
2.4.8.3	Installation of key equipment 3 ((specify which exactly)
2.4.8…..	……….. other
2.4.9	Civil works
2.4.9.1	Site preparation
2.4.9.2	Earthworks
2.4.9.3	Concrete and reinforced concrete works
2.4.9.4	Steel structure works
2.4.9.5	Finishing works
2.4.9…..	……….. other
2.4.10	Instrumentation works
2.4.10.1	Site preparation
2.4.10.2	Cable protection
2.4.10.3	Installation of instrumentation equipment
2.4.10.4	Installation of control cubicles
2.4.10.5	Laying and connecting cables to equipment
2.4.10.6	Process and electrical connection of instruments
2.4.10.7	Mounting the steering system
2.4.10.8	Testing installations
2.4.10.9	Testing instrumentation loops (loop test)
2.4.10…..	……….. other
2.4.11	Mechanical works
2.4.11.1	Site preparation
2.4.11.2	Installation and connection of pipelines
2.4.11.3	Testing of executed installations
2.4.11….	……….. other
2.4.12	Corrosion protection works
2.4.12.1	Site preparation
2.4.12…..	……….. other
2.4.13	Electric works
2.4.13.1	Site preparation
2.4.13.2	Cable protection
2.4.13.3	Laying earthing cables
2.4.13.4	Installation of electrical cabinets and equipment in the field
2.4.13.5	Laying and connecting cables to equipment
2.4.13.6	Testing installations
2.4.13…..	……….. other
2.4.14	Dismantling of scaffolding
2.4.15	Testing
2.4.16	Mechanical completion
2.4…..	……….. other
2.5	Technical inspections
2.6	Precommissoning
2.7	Commisioning
2.8	Start up
2.9	Test run
2.10	As built documentation
2.11	Trial Operation
3	PROJECT CLOSING
3.1	Technical review meeting
3.2	Use permit issuing
3.3	Takeover
3….	……….. other

## Instruction
INSTRUCTION FOR FILLING-IN THE REPORT BY THE EXTERNAL PARTNERS PER SUBJECT CONTRACT

1)	COVER SHEET

-	In cell B14 an official logo of the external partner shall be entered
-	In cell A22 there shall be stated a full title of the project, for which the progress report is prepared
-	In cell A30 a full title of the external partner shall be stated
-	In cell B46 a number of report / year shall be entered

2)	GENERAL OVERVIEW

-	In cells general characteristics related to the signed contract shall be entered: when it was signed, short summary of the contract subject- scope of work, external partners liabilities according to the subject contract, contract deadlines; summary of everything done so far related to the subject contract

3)	CONTRACT COST & SCHEDULE MANAGEMENT

-	In the "Contract number" cell contract number shall be entered (number in INA system)
-	In the "Supplier" cell a title of the external partner, with whom the Contract was made shall be stated
-	In the "Contracted amount" cell there shall be a full amount entered of the contract, concluded between INA and the external partner according to the subject contract
-	In the "Realized amount" cell there shall be a full amount per subject contract, realised at the end of the period, for which the report is prepared (design documentation supplied, works executed - in line with the method of payment defined by the subject contract)
-	In the "Realized / Contracted" cell nothing shall be entered. The cell is formated to present a display of spending funds per subject contract.
-	In cell "Kickoff meeting" the exact date shall be entered (format dd.mm.yy) when the kick off meeting between INA project team and the contractor was held
-	In cells "planned start, actual start, planned completion, actual completion", dates (format dd.mm.yy) for the actual completion shall be entered in the following way: / a) planned start and completion - dates shall be entered according to the submitted initial work schedule, which duration is defined by the subject contract; once entered, dates of planned start and completion shall not be changed any more / b) actual start - actual start date of work execution per subject contract shall be entered; upon the project completion (all project activities completed 100%) the contract conclusion date shall be entered in the "actual completion" cell
-	In cells "Planned duration, actual duration, delay from the planned completion" nothing shall be entered. Those cells are formated to show a totally planned and totally realised project duration in calendar days while cell "delay from the planned completion" upon completion of the final date (actual project completion) presents in chart and figures a delay related to the contracted duration - project completed ahead of schedule, slightly behind schedule or significantly behind schedule

	Invoicing plan (Payment milestones)

-	In cells "plan" submitting of planned invoices with regard to the contracted amount shall be distributed per months
-	In cells "actual" submitting of actual invoices per months (for reporting period)
-	In cells "difference" no entry to be made

4)	COMMUNICATION LIST

-	INA Project team members shall be listed along with their duties and positions on the project as well as company e-mail and cell phone number
-	In communication list there shall also be listed external partner team members with their duties and positions on the project as well as company e-mail and cell phone number

5)	MATERIAL & EQUIPMENT STATUS REPORT

-	For key equipment and material that are subject of contract is needed to fill in status of manufacturing, delivery, assembly followed by key milestone

6)	S-CURVE

-	Depending on the project development dynamics and scope of work (in agreement - decision with INA project implementation manager), the external partner has to prepare S-curve plan and report on the project progress on a daily, weekly, two-week i.e. monthly basis
-	For monthly reporting templates "S curve monthly" and "Input S curve - monthly" are used and if reported on a daily, weekly or two-week basis templates "S curve daily - weekly" and "Input S curve daily - weekly" are used

	S-CURVE - DAILY, WEEKLY, TWO-WEEK, MONTHLY

-	In the "PROJECT TITLE" cell it is necessary to enter a full project title, for which the report is prepared as well as the location
-	In the "CONTRACTOR AND CONTRACT NUMBER" cell it is necessary to enter a full title of the external partner (contractor) as well as the number of the contract, which is the reporting subject
-	In the "planned start, planned completion" cells dates shall be entered (format d.d.mm.yy), which are defined by the contract
-	In the "actual start, actual completion" actual dates (format d.d.mm.yy) shall be entered
-	In the "KEY ACTIVITIES IN THE SUBJECT PERIOD" cell there shall be a summary of what happened in the reported period (only what happened - key activities; for the reported period only: daily, weekly, two-week, monthly). Do not leave information from previous periods - the entire project history has to be stated in the "General overview" - Project general overview .
-	In the "KEY ACTIVITIES IN THE NEXT PERIOD" cell there shall be a summary of what is planned to be performed in the future period, for which the report is to be prepared (only key activities; for the reported period only: daily, weekly, two-week, monthly)

	MONTHLY S-CURVE

-	If reported on a monthly basis, initial data for the plan S-curve as well as the project progress on a monthly basis shall be entered in the template "Input S curve monthly"
-	In "planned %" cells data shall be entered on a monthly basis (last day of the month) as it is planned to have the project realisation developed. Once entered, data in these cells do not change untill the project completion; or according to the project manager decision (contract annex or similar - there shall be a written decision - approval)
-	In "actual %" it is necessary to enter data on a monthly basis (last day of the month) - project progress.

	S-CURVE - DAILY, WEEKLY, TWO-WEEK

-	If reported on a daily, weekly or two-week basis, initial data for the plan S-curve as well as the project progress shall be entered in the template "Input S curve - daily, weekly"
-	Depending on the period, for which the report is prepared, first of all it is necessary to select one option from the menu in cell E2
-	After that, in cell E5 there shall be entered a date of execution start (format d.d.mm.yy) and after that excel shall, based on the previously selected, prepare S-curve for reporting
-	In "planned %" cells it is necessary to enter data on a daily, weekly or two-week basis - depending on the reporting period (last day) as it is planned to have the project realisation developed. Once entered, data in these cells do not change untill the project completion; or according to the project manager decision (contract annex or similar - there shall be a written decision - approval)
-	In "actual %" it is necessary to enter data on a daily, weekly or two-week basis - depending on the reporting period (last day) - project progress.

7)	WORK SCHEDULE - GANTT CHART

-	In the template"Minimum Tracking activities" there is a list of activities, which represents a minimum, according to which an external parter has to prepare a work schedule in "MS Project" program and monitor the progress.
-	The external partner has to prepare a detailed work schedule (per activities) according to the scope of work, stated in the contract.
-	Depending on the scope (specific quality) of the project and in agreement with INA project implementation manager, list of minimum activities can be/must be expanded
-	According to the monitored activities, the external partner has to submit a work schedule, in which there is the following (per activities): initial planned start and completion (a total start and completion of the project have to respond to the dates listed in the contract, signed between INA and the external partner), completion percentage per activity and the actual start and the actual completion per each listed activity.

8)	PRINTING

-	Sheets to be printed: Cover sheet; General overview; Contract cost & schedule management; Material & equipment delivery status; Communication list; S curve - monthly or S curve daily - weekly (depending on agreed with INA Project manager)
-	Attach detailed work schedule prepared in MS Project